## Sheet1
Objectives | Start Date | Days to complete
Learn how to use the Unity 3D game engine by watching Brackey’s unity tutorials on YouTube. | 2022-10-24 | 14
Learn how to make 3D models using Blender by watching Blender Guru on YouTube. | 2022-10-26 | 4
Learn how to code in C# by watching a YouTube tutorial from Barnacules Nerdgasm. | 2022-11-07 | 14
Learn how to use Audacity and (Waveform 12 or LMMS) for the music and sounds in the game . | 2022-11-22 | 14
Learn how lighting and rendering works in unity by using the Unity Engine | 2022-12-06 | 14
With the knowledge from learning the Unity Game engine, I should make a minimal viable product. | 2022-12-19 | 28
Add sounds to the game, such as walking sounds, also add some music to the games and then show it to my supervisor for feedback | 2023-01-15 | 7
From the knowledge learnt from researching the lighting, add good lighting to the game and then show it to my supervisor for feedback. | 2023-01-20 | 28
Get a complete game working with all the different parts added together and try to fix as many bugs as possible. | 2023-02-15 | 20
Show the game to my supervisors and other people so they can give feedback to me about the game. | 2023-03-07 | 5

## Sheet2
Objectives | Start Date | Days to complete
Learn how to use the Unity 3D game engine by watching Brackey’s unity tutorials on YouTube then make a game map. | 2022-10-24 | 15
Learn how to make 3D models using Blender by watching Blender Guru on YouTube and make a character model. | 2022-11-02 | 15
Learn how to code in C# by watching a YouTube tutorial from Barnacules Nerdgasm and make a first-person controller script. | 2022-11-15 | 15
Design and implement the sound using audacity to ensure the game has appropriate sound | 2022-11-29 | 15
Learn how lighting and rendering works in unity by using the Unity Engine | 2022-12-14 | 30
With the knowledge from learning the Unity Game engine, I should make a minimal viable product. | 2023-01-14 | 30
Add sounds to the game, such as walking sounds, also add some music to the games and then show it to my supervisor for feedback | 2023-02-14 | 7
From the knowledge learnt from researching the lighting, add good lighting to the game and then show it to my supervisor for feedback. | 2023-02-21 | 30
Get a complete game working with all the different parts added together and try to fix as many bugs as possible. | 2023-03-21 | 20
Show the game to my supervisors and other people so they can give feedback to me about the game. | 2023-04-10 | 5